## Taul1
The goal is to develop an application, which students and teachers can use to track student learning progress in courses. Teacher can create course X, add students there,define course schedule and learning progress tracking. After this the student can sign in, see ongoing courses and mark his learning progress with a traffic light system. Teacher can see a summary of a course situation. The tool will send automatic notifications for marking learning progress. The tool will send learning progress summary notifications for teacher.
Summer Project Course System APP
Date | Hours | Phase | Tasks | Deliverables | Other
16/05-20/05 | 27 | Plan | Requirement Analysis | a design document including following information about the app: Introduction Basic structure of UI Basic structure of Database Programming languages, tools, publish and so on Development plans | weely report
System Design
23/05-27/05 | 27 | Execution | UI designment | all of the .html files needed in the design document
30/05-03/06 | 27 |  | JS event (object-oriented) | all of the .js files needed in the .html files
06/06-10/06 | 27 |  | Server and API , Database | Server.js file used to connect the .html and database, make all the functions work
13/06-17/06 | 27 | Launching | publish and test and modify | a qualified published web app
20/06 | 6 |  | closing report | closing report document